## Sheet1
AI for Environmental Monitoring & Urban Planning - Project Gantt Chart
Project Start: 17 Oct 2025
Project End: 17 Apr 2026
Team: Sabal Nemkul ¦ Thathsara Abesooriya ¦ Syed Bokhari
SPRINT / TASK | OWNER | START | END | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17
◆ SPRINT 0 — INITIATION & PLANNING (17 Oct – 21 Nov 2025) |  | 2025-10-17 | 2025-11-21 | █ | █ | █ | █ | █ | █
Create Mind Map | Sabal | 2025-10-17 | 2025-10-24 | █ | █
Produce OKR Table | Syed Bokhari | 2025-10-17 | 2025-10-24 | █ | █
Draft Project Charter | Thathsara | 2025-10-24 | 2025-11-07 |  | █ | █ | █
Complete Risk Assessment | Sabal | 2025-10-24 | 2025-11-07 |  | █ | █ | █
Create Communication Plan | Sabal | 2025-11-07 | 2025-11-14 |  |  |  | █ | █
Produce Ishikawa Diagram | Syed Bokhari | 2025-11-07 | 2025-11-21 |  |  |  | █ | █ | █
◆ SPRINT 1 — RESEARCH & DESIGN (26 Nov – 14 Jan 2026) |  | 2025-11-26 | 2026-01-14 | [6 empty] | █ | █ | █ | █ | █ | █ | █
Research Dashboard Design | Sabal | 2025-11-26 | 2025-12-05 | [6 empty] | █ | █
Research Anomaly Visualisation | Syed Bokhari | 2025-11-26 | 2025-12-10 | [6 empty] | █ | █
Research GIS Layers & Mapping | Thathsara | 2025-11-26 | 2025-12-10 | [6 empty] | █ | █
Produce Dashboard Wireframes | Sabal | 2025-12-05 | 2025-12-19 | [7 empty] | █ | █ | █
Create Use Case Diagrams | Sabal | 2025-12-10 | 2025-12-24 | [8 empty] | █ | █
Create Activity Diagrams | Sabal | 2025-12-24 | 2026-01-14 | [10 empty] | █ | █ | █
◆ SPRINT 2 — PROTOTYPE DEVELOPMENT (16 Jan – 06 Mar 2026) |  | 2026-01-16 | 2026-03-06 | [13 empty] | █ | █ | █ | █ | █ | █ | █ | █
Explore Datasets | Syed Bokhari | 2026-01-16 | 2026-01-30 | [13 empty] | █ | █ | █
Test CV Model Options | Thathsara | 2026-01-16 | 2026-02-06 | [13 empty] | █ | █ | █ | █
Begin Dashboard Layout Prototype | Sabal | 2026-01-30 | 2026-02-13 | [15 empty] | █ | █ | █
Define Integration Requirements | Sabal | 2026-02-13 | 2026-02-20 | [17 empty] | █ | █
Prepare Data Pipeline Outline | Syed Bokhari | 2026-02-13 | 2026-03-06 | [17 empty] | █ | █ | █ | █
◆ SPRINT 3 — EVALUATION & REFINEMENT (08 Mar – 10 Apr 2026) |  | 2026-03-08 | 2026-04-10 | [21 empty] | █ | █ | █ | █ | █
Refine Anomaly Visualisation | Thathsara | 2026-03-08 | 2026-03-20 | [21 empty] | █ | █
Improve Dashboard Interactions | Sabal | 2026-03-08 | 2026-03-22 | [21 empty] | █ | █
Improve Detection Details Panel | Syed Bokhari | 2026-03-08 | 2026-03-22 | [21 empty] | █ | █
Integrate & Refine Heatmap Overlay | Sabal | 2026-03-22 | 2026-04-03 | [23 empty] | █ | █
Prepare Summary Report Logic | Syed Bokhari | 2026-03-22 | 2026-04-10 | [23 empty] | █ | █ | █
◆ SPRINT 4 — FINALISATION & REPORTING (10 Apr – 17 Apr 2026) |  | 2026-04-10 | 2026-04-17 | [25 empty] | █
Finalise Summary Report Output | Syed Bokhari | 2026-04-10 | 2026-04-13 | [25 empty] | █
Finalise Wireframes for Appendix | Sabal | 2026-04-10 | 2026-04-13 | [25 empty] | █
Finalise Use Case Diagrams | Sabal | 2026-04-10 | 2026-04-14 | [25 empty] | █
Finalise Activity Diagrams | Thathsara | 2026-04-10 | 2026-04-14 | [25 empty] | █
Write Final Report | Sabal | 2026-04-10 | 2026-04-16 | [25 empty] | █
Prepare Group Poster | Syed Bokhari | 2026-04-10 | 2026-04-16 | [25 empty] | █
Prepare Presentation Slides | Sabal & Thathsara | 2026-04-13 | 2026-04-17
◆ SUBMISSION DEADLINE |  | 2026-04-17 | 2026-04-17
◆ EXHIBITION / DEMO DAY |  | 2026-04-21 | 2026-04-21