## Project Planner
Project Planner
Start Date :- 17/10/2025 | End date :- 10/04/2026 |  |  | Period Highlight: |  | 0 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION (Weeks) | ACTUAL DURATION | PERCENT COMPLETE | Actual Start | Weeks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project Initiation | 1 | 4 |  | 75% | 1
Research: Urban AI Systems | 3 | 2 | 2 | 100% | 3
Define Aims, Objectives, OKRs | 2 | 2 | 2 | 100% | 2
Finalize Project Charter | 2 | 2 |  | 60% | 2
Research: CCTV & Drone Data Sources | 3 | 2 |  | 0% | 3
Data Collection | 4 | 2 |  | 0%
Clean Data | 6 | 1 |  | 0%
Model Development & Training | 7 | 6 |  | 0%
Research: Object Detection Models | 7 | 2 |  | 0%
Train & Validate Models (KR2.1) | 9 | 4 |  | 0%
Implement Anomaly Detection (KR2.2) | 12 | 2 |  | 0%
System Integration | 14 | 4 |  | 0%
Integrate CV Models with Video | 14 | 2 |  | 0%
GIS Integration (KR1.4) | 16 | 2 |  | 0%
Dashboard & Visualization Development | 18 | 4 |  | 0%
Research: Environmental Dashboards | 18 | 1 |  | 0%
Build Dashboard & Reporting Tools (KR4.1) | 19 | 2 |  | 0%
Testing, Evaluation & Deployment | 21 | 2 |  | 0%
Proof-of-Concept Testing (KR2.3) | 23 | 1 |  | 0%
User Testing with Council Officers (KR4.4) | 24 | 1 |  | 0%